## POA
Sr No | Task | Date | Start Time | Date | End Time | Time(Min) | Owner | Remarks
1 | Take FULL backup of all User databases on RGIPIRPASAG01 | 2024-03-07 | 8:00 | 2024-03-07 | 9:30 | 90 | DBA | Done
2 | Copy FULL backup of all User databases on IRPASPRDBAG,IRPASDRDBAG | 2024-03-07 | 9:30 | 2024-03-07 | 21:30 | 720 | INFRA | Done
3 | Restore all user databases in Restoring mode on all 2 new SQL Servers | 2024-03-07 | 9:30 | 2024-03-07 | 12:00 | 210 | DBA | WIP
4 | Create all Linked Server, Server Triggers, Server Audit on all 2 new SQL Servers | 2024-03-07 | 12:00 | 2024-03-07 | 13:00 | 60 | DBA | Done
5 | DB Mail Config and verification on all 2 new SQL Servers | 2024-03-07 | 12:00 | 2024-03-07 | 13:00 | 60 | DBA | Done
6 | Resize all 2 new servers with resources as per server request raised | 2024-03-07 | 20:00 | 2024-03-07 | 20:30 | 30 | INFRA | Done
7 | Disable and remove Replication configuration from RGIPIRPASAG01 to RGIDWHDB02 | 2024-03-08 | 23:00 | 2024-03-08 | 23:30 | 30 | DBA
8 | Stop Application, Biztalk Integrations, Disable SQL Logins | 2024-03-08 | 23:30 | 2024-03-08 | 23:45 | 15 | App Team & DBA | Downtime Starts | D
9 | Change both DNS (RGIiRPasDbAG.reliancegeneral.co.in) & (RGIIRPASRead.reliancegeneral.com) pointing to new Primary server | 2024-03-08 | 23:45 | 2024-03-09 | 0:00 | 15 | INFRA | Can Be Done Simultaneously | D
10 | Take DIFFERENTIAL Backup for all user databases | 2024-03-09 | 0:00 | 2024-03-09 | 1:30 | 90 | DBA |  | D
11 | Copy DIFF backup files on all 2 new SQL Servers | 2024-03-09 | 1:30 | 2024-03-09 | 2:00 | 30 | INFRA |  | D
12 | Restore all DIFFERENTIAL backups on New Primary | 2024-03-09 | 2:00 | 2024-03-09 | 3:30 | 90 | DBA |  | D
13 | Create XML Compression Assembly in all 2 new SQL Servers | 2024-03-09 | 3:30 | 2024-03-09 | 3:45 | 15 | DBA & App Team |  | D
14 | Sync all SQL Logins on New Servers | 2024-03-09 | 3:30 | 2024-03-09 | 3:45 | 15 | DBA |  | D
15 | Verification of database accessibility from Applications(Application Verification) | 2024-03-09 | 3:45 | 2024-03-09 | 4:00 | 15 | App Team, QA Team | Database will be accessible for App Testing | D
16 | Application Downtime ENDS | 2024-03-09 | - | 2024-03-09 | 4:00 | - | App Team |  | D
17 | Configure 7 User DB's in AlwaysOn Configuration | 2024-03-09 | 4:00 | 2024-03-09 | 8:00 | 240 | DBA |  | D
18 | Create App specific SQL Jobs on all 2 new servers | 2024-03-09 | 3:45 | 2024-03-09 | 4:00 | 15 | DBA |  | D
19 | Verification and status change(Enable/Disable) SQL Jobs on all 2 new SQL Servers | 2024-03-09 | 3:45 | 2024-03-09 | 4:00 | 15 | App Team |  | D
20 | Start Full DB Index Rebuild and Updatestats for transactional databases | 2024-03-09 | 4:00 | 2024-03-09 | - | 900 | DBA |  | WIP
21 | Pointing of readonly dns (RGIIRPASRead.reliancegeneral.com) to Read-only Replica | 2024-03-09 | 8:00 | 2024-03-09 | 8:15 | 15 | INFRA |  | D
22 | Addition of Servers in Windows monitoring utility | 2024-03-09 | 8:00 | 2024-03-09 | 9:00 | 60 | INFRA |  | D
23 | SQL Backup configuration in Azure Workload backup | 2024-03-09 | 8:00 | 2024-03-09 | 9:00 | 60 | DBA |  | D
24 | SQL Replication Configuration from IRPASPRDBAG to DWHDB02 | 2024-03-09 | 9:00 | 2024-03-10 | 22:00 | 2220 | DBA |  | WIP
Application Team to adopt New Database DNS by 22nd March 2024

## Team
Owner | Contact person / contact number
DBA | Amol Bhagat: 8689808678
INFRA | Hemant Bhogle: 7977662851
APP TEAM | Parasd Kulkarni: 9403372292 Manohar Molawade: 8108206441 Akshay Dhumal: 9769533997
QA | Raghu: 7032973793 Bhagyashri: 9987078635

## DNS
Server IP | Hostname | FQDN | Purpose | Remarks
10.62.190.126 | IRPASPRDBAG | IRPASPRDBAG.brobot.com | IRPAS Read\Write | Have arcos raised for team members
10.62.174.133 | IRPASDRDBAG | IRPASDRDBAG.brobot.com | IRPAS Read-Only
10.62.190.180 | IRPASLSN | IRPASLSN.BROBOT.COM (RGIiRPasDbAG.reliancegeneral.co.in) | App will connect to Read/Write replica using this FQDN (Preferred) | DNS will be created while configuring Always On Group Listner
10.62.174.132
10.62.174.133 |  | IRPASREAD.BROBOT.COM (RGIIRPASRead.reliancegeneral.com) | App will connect to Read Only Replica using this FQDN | New Brobot DNS need to be create with Infra Help

## Backup Details
Database | AG | FULL Size (GB) | Time(Min) | DIFF Size (GB) | Time (Min) | Read\Write Replica | Read Only Replica
IRPAS | YES | 540 | 240 | 55 | 20 | In AG | In AG
DashboardDWH | YES | 60 | 25 | 2 | 5 | In AG | In AG
Corporate_Portal | YES | 0.7 | 1 | 0.01 | 1 | In AG | In AG
ActivityTracker | YES | 0.01 | 1 | 0.01 | 1 | In AG | In AG
iRPAS_EXTERNAL | YES | 0.8 | 1 | 0.8 | 1 | In AG | In AG
IRPASCustomerPortal | YES | 1 | 2 | 0.5 | 1 | In AG | In AG
PPHC | YES | 0.06 | 1 | 0.01 | 1 | In AG | In AG
audittrail | NO | 15 | 5 | 1 | 5 | From Old Primary to New Primary | From Old DR to New DR
AuditTrailMQ | NO | 25 | 10 | 0.1 | 5 | From Old Primary to New Primary | From Old DR to New DR
AuditTrailMQ_New | NO | 920 | 180 | 10 | 10 | From Old Primary to New Primary | From Old DR to New DR
imd_tables_for_migration | NO | 0.7 | 5 | 0.01 | 1 | From Old Primary to New Primary | From Old DR to New DR
irpas_temp | NO | 7 | 5 | 0.5 | 2 | From Old Primary to New Primary | From Old DR to New DR
RPAS_Existing | NO | 0.6 | 5 | 0.01 | 1 | From Old Primary to New Primary | From Old DR to New DR
RPASINCREMENTAL | NO | 0.6 | 5 | 0.01 | 1 | From Old Primary to New Primary | From Old DR to New DR
EventNotifications | NO |  |  |  |  | From Old Primary to New Primary | NA
IRPAS_Archive | NO | 2 | 5 | 0.04 | 1 | From Old Primary to New Primary | NA
Total Size |  | 1572.87 | 491 | 70 | 56